## Sheet2
| Likelihood | Impact | Risk
Muchen become hostile | 1 | 1 | 1
FPGA logic capacity is not enough to implement our solution. | 0.5 | 1 | 0.5
Electronics and battery are too heavy for the drone to take off. | 0.5 | 1 | 0.5
Drone cannot take off at all due to drone hardware failure. | 0.5 | 1 | 0.5
Accidents that damage to drone and FPGA that leads to extra budget that we may not have. | 0.7 | 0.7 | 0.49
Forced to buy cheaper components which leads to lower performance. | 0.8 | 0.5 | 0.4
Deliveries is not meeting client’s expectations | 0.2 | 0.8 | 0.4
Knowledge and skill (Machine Learning & Computer vision) required for project is not sufficient. | 0.5 | 0.8 | 0.4
Our scrum method is not efficient | 0.5 | 0.7 | 0.35
Scope of the project is underestimated which leads to burn outs | 0.5 | 0.7 | 0.35
Not have enough money. | 0.5 | 0.7 | 0.35
Not enough time commitment from team member due to other courses. | 0.5 | 0.6 | 0.3
Team is indecisive which leads to delay - management is not good enough to make a timely decision. | 0.4 | 0.7 | 0.28
Team has lack of communication and make assumptions which leads to incompatibility | 0.4 | 0.7 | 0.28
Documentation is not specific / complete. | 0.7 | 0.4 | 0.28
Not enough time to work on documentation. | 0.7 | 0.4 | 0.28
Peter become hostile | 0.5 | 0.5 | 0.25
Scope of the project is overestimated which leads to diversification of vision of the project. | 0.5 | 0.5 | 0.25
Not enough machine learning training data. | 0.5 | 0.5 | 0.25
Arthur becomes hostile | 0.5 | 0.5 | 0.25
Wilson becomes hostile | 0.5 | 0.5 | 0.25
Illegal to fly drone. | 0.3 | 0.8 | 0.24
New technology or research that changes the scope significantly | 0.3 | 0.7 | 0.21
Technical debt paydown impact project timeline. | 0.4 | 0.5 | 0.2
Software license does not allow our application to be delivered. | 0.3 | 0.6 | 0.18
Key hardware components not available | 0.2 | 0.8 | 0.16
Machine learning resources lack documentation | 0.3 | 0.5 | 0.15
Camera lack documentation | 0.3 | 0.5 | 0.15
FPGA lack documentation | 0.3 | 0.5 | 0.15
Delivered documentation not adequate for usage and upgrade. | 0.5 | 0.3 | 0.15
Selected software methodology creates issues with team member that decreases productivity | 0.2 | 0.7 | 0.14
Legal changes significantly affect project - drones in particular | 0.2 | 0.7 | 0.14
The final product cannot be maintained or extended. | 0.7 | 0.2 | 0.14
Client becoming hostile | 0.2 | 0.7 | 0.14
Client wants to modify scope and requirements that leads to delays or cut features. | 0.2 | 0.6 | 0.12
Development environment is inadequate. | 0.2 | 0.6 | 0.12
Sabotage | 0.1 | 1 | 0.1
Loss of client | 0.1 | 1 | 0.1
Loss of team member | 0.1 | 0.9 | 0.09
Equipment shipment is delayed or lost. | 0.1 | 0.8 | 0.08
Client is not available enough to provide significant help. | 0.1 | 0.5 | 0.05
Competitive offerings affect project requirement | 0.1 | 0.5 | 0.05
Camera doesn’t work with FPGA | 0.1 | 0.5 | 0.05
FPGA doesn’t work with transmission systems | 0.1 | 0.5 | 0.05
Ardell becomes hostile | 0 | 0 | 0